## About
Worksheets
Document ID |  | <File Name>
Purpose |  | Project plan. > High level Business requirements - Details business need broken out into key elements > High level Deliverables - What needs to be created > High levl delivery plan This project plan is to be used to put a framework for the agile build process. It should define the sprint period (Iteration to get first working product), help in providing and estimate of the final solution and support the management of scope creep.
User | Date | Version | Comment | DataAssetRegistry
SolutionRegistry

## Business Requirements
ID | Business requirement | Owner | Solution Description | Benefits of solution approach | Status
<Ref> | <Description of the unique Business requierment> | <Business owner for the requirement> | <What is the proposed solution for the bussiness requirement> | <Why this solution approach is taken> | <Proposed / Approved>
BR-01 | Identify common pairings of items that customers are purchasing in a single transaction. | TES | Use the point of sale data from the previous day's trading to isolate common pairings of high value items. We will consider only transactions where a top 25 item has been bought and use the FP Growth algorithm to analyse the common pairings with other items. Top 25 is defined by [volume] x [unit price] where [unit price] >= €7 | From speaking with the Primark store manager it is clear that, although there is a good understanding of the KPIs and trends throughout the day, there is not a lot of clarity around what items sell well with other items. By providing a mechanism whereby these frequent item sets are identified, volume of sales, average basket value and ultimately margin can be increased. | Proposed
BR-02 | Make BR-01 form part of their daily reporting pack. | TES | Build an interactive dashboard which displays the KPIs and associated item sets for the top 25 items as defined by the BR01. Item sets for a given top 25 item can be displayed in tabular format or in graphical format using a spider diagram | Provides a quick and easy way for the store manager to identify pairings of items that should go together. | Proposed
BR-03 | Use information from BR01 to redefine store layout and arrange items by pairing. | Andrew | The store manager uses the information displayed on the dashboard to rearrange items on the shop floor according to the item sets suggested by the model. |  | Proposed
Defines the business requirements who owns them and how we propose to solve these requirements in our solution.
Each requirement should be unique and explicit in its purpose.
Each requirement needs to be approved by the business.

## Product Description
ID | Type | Product name | Product Description | Business requirements supported
<Ref> | <Final / Component> Final = Final product delivered Component = Component is a product that makes up part of the final solution but is sufficient to be consided a delivered component in its own right | <Unique product name> | <Product description> | <List of Busienss requiremetns supported>
PD-01 | Component | Rapidminer Process | Process deployed to isolate frequent items | BR-01
PD-02 | Component | Report database | Storage and transformation of tables | BR-01/BR-02
PD-03 | Final | Report web portal | Publish reports and any additional views | BR-02
PD-04 | Component | User administration | Create and maintain user access rights | BR-03
Defines the 'Lego Blocks' that make up the solution and how these 'Lego blocks' connect with the busienss reuqirements agreed

## Delivery plan
ID | Task | Owner | Effort (days)
IT_CC-01 | Create database structure | Aaron | 1
IT_CC-02 | Create working RapidMiner process on POC Data | Aaron | 1
IT_CC-03 | Test RapidMiner Process on a further weeks data | Aaron | 2
IT_CC-04 | Create web portal design (Balsamiqu and excel) | Michael | 1
IT_CC-05 | Build web portal | Naimish | 2
IT_CC-06 | Create user admin structure | Naimish/Michael | 1
IT_CC-07 | Create Presentation of results for Primark | Thomas/Aaron/Michael | 1
IT_CC-08 | Run model over 3 week testing period | Aaron/Michael | 15
IT_CC-09 | Test loading and publishing | Aaron/Michael | 2
IT_CC-10 | Evaluate the ROI of using the model for Primark | Aaron/Michael | 2
Total
Provides a logical story of the key tasks that need to be completed in order for the solution to be delivered.
Each task needs to have an associated number of days for delivery.